## Sheet1
| Type | Division | Meeting | Priority | ProjectCode | Description | AuthorityEmployeeCode | AssigneesEmployeeCodes | DateOfMeeting | DateOfAssignment | ScheduleDate | DueDate | NoOfDays | ScheduleTimeHrs | ScheduleTimeMins | NoOfHrs
1 | Project | Project Management |  |  | 26/010/750 | 1. Project Initiation Phase Project handover to PMU after contract agreement | Nirodha | Bhavika |  | 2026-05-28 | 2026-05-29 | 2026-05-30
2 | Project | Project Management |  |  | 26/010/750 | 1. Project Initiation Phase Document handover from Project Proposal Unit | Nirodha | Bhavika |  | 2026-05-28 | 2026-05-30 |  | 5
3 | Project | Project Management |  |  | 26/010/750 | 1. Project Initiation Phase Assign suitable Project Manager | Nirodha | Nirodha |  | 2026-05-28 | 2026-05-31 |  | 7
4 | Project | Project Management |  |  | 26/010/750 | 1. Project Initiation Phase Initial meeting with Proposal Unit + PMU | Nirodha | Nivedha |  | 2026-05-28 | 2026-06-01 | 2026-06-02
5 | Project | Project Management |  |  | 26/010/750 | 1. Project Initiation Phase Initial meeting with Management + PMU + Proposal Unit | Nirodha | Nivedha |  | 2026-05-28 |  |  | 2
6 | Project | Project Management |  |  | 26/010/750 | 1. Project Initiation Phase Preparation of working budget | Nirodha | Nivedha |  | 2026-05-28 |  |  | 1
7 | Project | Project Management |  |  | 26/010/750 | 1. Project Initiation Phase Preparation of consultant contracts | Nirodha | Nivedha |  | 2026-05-28 |  |  | 3
8 | Project | Project Management |  |  | 26/010/750 | 1. Project Initiation Phase Handover to consultants | Nirodha | Nivedha |  | 2026-05-28 |  |  | 4
9 | Project | Project Management |  |  | 26/010/750 | 1. Project Initiation Phase Initial meeting with TL and EML team | Nirodha | Nivedha |  | 2026-05-28 |  |  | 5
10 | Project | Project Management |  |  | 26/010/750 | 1. Project Initiation Phase Internal kick-off meeting | Nirodha | Nivedha |  | 2026-05-28 |  |  | 1
11 | Project | Project Management |  |  | 26/010/750 | 1. Project Initiation Phase Client kick-off meeting | Nirodha | Nivedha |  | 2026-05-28 |  |  | 1
13 | Project | Project Management |  |  | 26/010/750 | 2. Inception & Planning Phase Information required from client identified | Nirodha | Nivedha |  | 2026-05-28 |  |  | 1
14 | Project | Project Management |  |  | 26/010/750 | 2. Inception & Planning Phase Information request submission to client | Nirodha | Nivedha |  | 2026-05-28 |  |  | 1
15 | Project | Project Management |  |  | 26/010/750 | 2. Inception & Planning Phase Initial site visit | Nirodha | Nivedha |  | 2026-05-28 |  |  | 1
16 | Project | Project Management |  |  | 26/010/750 | 2. Inception & Planning Phase Inception report preparation | Nirodha | Nivedha |  | 2026-05-28 |  |  | 1
17 | Project | Project Management |  |  | 26/010/750 | 2. Inception & Planning Phase Internal review of inception report | Nirodha | Nivedha |  | 2026-05-28 |  |  | 1
18 | Project | Project Management |  |  | 26/010/750 | 2. Inception & Planning Phase Submission of inception report | Nirodha | Nivedha |  | 2026-05-28 |  |  | 1
19 | Project | Project Management |  |  | 26/010/750 | 2. Inception & Planning Phase Client feedback received | Nirodha | Nivedha |  | 2026-05-28 |  |  | 1
20 | Project | Project Management |  |  | 26/010/750 | 2. Inception & Planning Phase Address comments and revise inception report | Nirodha | Nivedha |  | 2026-05-28 |  |  | 1
21 | Project | Project Management |  |  | 26/010/750 | 2. Inception & Planning Phase Invoice preparation and submission | Nirodha | Nivedha |  | 2026-05-28 |  |  | 1
22 | Project | Project Management |  |  | 26/010/750 | 2. Inception & Planning Phase Payment follow-up and receipt | Nirodha | Nivedha |  | 2026-05-28 |  |  | 1
24 | Project | Project Management |  |  | 26/010/750 | 3. Field Work & Stakeholder Engagement Phase Stakeholder identification | Nirodha | Nivedha |  | 2026-05-28 |  |  | 1
25 | Project | Project Management |  |  | 26/010/750 | 3. Field Work & Stakeholder Engagement Phase Stakeholder mapping | Nirodha | Nivedha |  | 2026-05-28 |  |  | 1
26 | Project | Project Management |  |  | 26/010/750 | 3. Field Work & Stakeholder Engagement Phase KII scheduling | Nirodha | Nivedha |  | 2026-05-28 |  |  | 1
27 | Project | Project Management |  |  | 26/010/750 | 3. Field Work & Stakeholder Engagement Phase Conduct stakeholder/KII meetings | Nirodha | Nivedha |  | 2026-05-28 |  |  | 1
28 | Project | Project Management |  |  | 26/010/750 | 3. Field Work & Stakeholder Engagement Phase Meeting minutes preparation | Nirodha | Nivedha |  | 2026-05-28 |  |  | 1
29 | Project | Project Management |  |  | 26/010/750 | 3. Field Work & Stakeholder Engagement Phase Workshop stakeholder identification | Nirodha | Nivedha |  | 2026-05-28 |  |  | 1
30 | Project | Project Management |  |  | 26/010/750 | 3. Field Work & Stakeholder Engagement Phase Logistic arrangements | Nirodha | Nivedha |  | 2026-05-28 |  |  | 1
31 | Project | Project Management |  |  | 26/010/750 | 3. Field Work & Stakeholder Engagement Phase Workshop material preparation | Nirodha | Nivedha |  | 2026-05-28 |  |  | 1
32 | Project | Project Management |  |  | 26/010/750 | 3. Field Work & Stakeholder Engagement Phase Workshop conducting | Nirodha | Nivedha |  | 2026-05-28 |  |  | 1
33 | Project | Project Management |  |  | 26/010/750 | 3. Field Work & Stakeholder Engagement Phase Workshop report preparation | Nirodha | Nivedha |  | 2026-05-28 |  |  | 1
34 | Project | Project Management |  |  | 26/010/750 | 3. Field Work & Stakeholder Engagement Phase Survey design | Nirodha | Nivedha |  | 2026-05-28 |  |  | 1
35 | Project | Project Management |  |  | 26/010/750 | 3. Field Work & Stakeholder Engagement Phase Questionnaire preparation | Nirodha | Nivedha |  | 2026-05-28 |  |  | 1
36 | Project | Project Management |  |  | 26/010/750 | 3. Field Work & Stakeholder Engagement Phase Enumerator identification | Nirodha | Nivedha |  | 2026-05-28 |  |  | 1
37 | Project | Project Management |  |  | 26/010/750 | 3. Field Work & Stakeholder Engagement Phase Enumerator training | Nirodha | Nivedha |  | 2026-05-28 |  |  | 1
38 | Project | Project Management |  |  | 26/010/750 | 3. Field Work & Stakeholder Engagement Phase Survey implementation | Nirodha | Nivedha |  | 2026-05-28 |  |  | 1
39 | Project | Project Management |  |  | 26/010/750 | 3. Field Work & Stakeholder Engagement Phase Survey data cleaning | Nirodha | Nivedha |  | 2026-05-28 |  |  | 1
40 | Project | Project Management |  |  | 26/010/750 | 3. Field Work & Stakeholder Engagement Phase Survey analysis | Nirodha | Nivedha |  | 2026-05-28 |  |  | 1
41 | Project | Project Management |  |  | 26/010/750 | 3. Field Work & Stakeholder Engagement Phase Air quality assessment | Nirodha | Nivedha |  | 2026-05-28 |  |  | 1
42 | Project | Project Management |  |  | 26/010/750 | 3. Field Work & Stakeholder Engagement Phase Noise assessment | Nirodha | Nivedha |  | 2026-05-28 |  |  | 1
43 | Project | Project Management |  |  | 26/010/750 | 3. Field Work & Stakeholder Engagement Phase Water quality assessment | Nirodha | Nivedha |  | 2026-05-28 |  |  | 1
44 | Project | Project Management |  |  | 26/010/750 | 3. Field Work & Stakeholder Engagement Phase Biodiversity assessment | Nirodha | Nivedha |  | 2026-05-28 |  |  | 1
45 | Project | Project Management |  |  | 26/010/750 | 3. Field Work & Stakeholder Engagement Phase GIS mapping | Nirodha | Nivedha |  | 2026-05-28 |  |  | 1
46 | Project | Project Management |  |  | 26/010/750 | 3. Field Work & Stakeholder Engagement Phase Laboratory coordination | Nirodha | Nivedha |  | 2026-05-28 |  |  | 1
48 | Project | Project Management |  |  | 26/010/750 | 4. Reporting & Review Phase Internal technical meetings | Nirodha | Nivedha |  | 2026-05-28 |  |  | 1
49 | Project | Project Management |  |  | 26/010/750 | 4. Reporting & Review Phase Client coordination meetings | Nirodha | Nivedha |  | 2026-05-28 |  |  | 1
50 | Project | Project Management |  |  | 26/010/750 | 4. Reporting & Review Phase Draft report preparation | Nirodha | Nivedha |  | 2026-05-28 |  |  | 1
51 | Project | Project Management |  |  | 26/010/750 | 4. Reporting & Review Phase Internal QA/QC review | Nirodha | Nivedha |  | 2026-05-28 |  |  | 1
52 | Project | Project Management |  |  | 26/010/750 | 4. Reporting & Review Phase Draft report submission | Nirodha | Nivedha |  | 2026-05-28 |  |  | 1
53 | Project | Project Management |  |  | 26/010/750 | 4. Reporting & Review Phase Client feedback received | Nirodha | Nivedha |  | 2026-05-28 |  |  | 1
54 | Project | Project Management |  |  | 26/010/750 | 4. Reporting & Review Phase Address draft report comments | Nirodha | Nivedha |  | 2026-05-28 |  |  | 1
55 | Project | Project Management |  |  | 26/010/750 | 4. Reporting & Review Phase Invoice preparation for draft report | Nirodha | Nivedha |  | 2026-05-28 |  |  | 1
56 | Project | Project Management |  |  | 26/010/750 | 4. Reporting & Review Phase Payment receipt for draft report | Nirodha | Nivedha |  | 2026-05-28 |  |  | 1
57 | Project | Project Management |  |  | 26/010/750 | 4. Reporting & Review Phase Final report preparation | Nirodha | Nivedha |  | 2026-05-28 |  |  | 1
58 | Project | Project Management |  |  | 26/010/750 | 4. Reporting & Review Phase Final internal QA/QC | Nirodha | Nivedha |  | 2026-05-28 |  |  | 1
59 | Project | Project Management |  |  | 26/010/750 | 4. Reporting & Review Phase Final report submission | Nirodha | Nivedha |  | 2026-05-28 |  |  | 1
60 | Project | Project Management |  |  | 26/010/750 | 4. Reporting & Review Phase Client final comments received | Nirodha | Nivedha |  | 2026-05-28 |  |  | 1
61 | Project | Project Management |  |  | 26/010/750 | 4. Reporting & Review Phase Address final comments | Nirodha | Nivedha |  | 2026-05-28 |  |  | 1
62 | Project | Project Management |  |  | 26/010/750 | 4. Reporting & Review Phase Final report resubmission | Nirodha | Nivedha |  | 2026-05-28 |  |  | 1
64 | Project | Project Management |  |  | 26/010/750 | 5. Project Closure Phase Final invoice preparation | Nirodha | Nivedha |  | 2026-05-28 |  |  | 1
65 | Project | Project Management |  |  | 26/010/750 | 5. Project Closure Phase Final payment follow-up | Nirodha | Nivedha |  | 2026-05-28 |  |  | 1
66 | Project | Project Management |  |  | 26/010/750 | 5. Project Closure Phase Receive final payment | Nirodha | Nivedha |  | 2026-05-28 |  |  | 1
67 | Project | Project Management |  |  | 26/010/750 | 5. Project Closure Phase Project completion documentation | Nirodha | Nivedha |  | 2026-05-28 |  |  | 1
68 | Project | Project Management |  |  | 26/010/750 | 5. Project Closure Phase Lessons learned meeting | Nirodha | Nivedha |  | 2026-05-28 |  |  | 1
69 | Project | Project Management |  |  | 26/010/750 | 5. Project Closure Phase Project closure meeting with management | Nirodha | Nivedha |  | 2026-05-28 |  |  | 1
70 | Project | Project Management |  |  | 26/010/750 | 5. Project Closure Phase Archive project documents | Nirodha | Nivedha |  | 2026-05-28 |  |  | 1
71 | Project | Project Management |  |  | 26/010/750 | 5. Project Closure Phase Client satisfaction feedback | Nirodha | Nivedha |  | 2026-05-28 |  |  | 1
72 | Project | Project Management |  |  | 26/010/750 | 5. Project Closure Phase PM performance evaluation | Nirodha | Nivedha |  | 2026-05-28 |  |  | 1